## Sheet1
Task | Draft Implemented | Draft Verified | Subtask | Owner | Pages from Original Document
1 | BIRD202.2 Draft 1 | BIRD202.2 Draft 6 | Clarify use of "connected" throughout document (e.g., use of signal_names, distinction vs. "shorted") | Bob Ross
2 | (done; confirm draft #) | Draft 29 | Adding structural diagrams of an EMD (three), featuring extended net examples (text on page 7) | Randy Wolff |  | not needed
3 |  | Draft 29 | EMD Model and Supply Pin Connections - replace "Pins may be terminals…" with new section from owner | Bob Ross | 26
4 |  |  | List of key terms and definitions | Michael Mirmak
5 |  | Draft 29 | Check of syntax of examples throughout the document | (all) |  | Review 13.7
6 |  | Draft 29 | Reorder rules in [EMD Group] (e.g., I/O pin_name rules) to appear after the definitions of terms used | Bob Ross | 14, 15 | (requires confirmation; may be in 13.6)
7 | Draft 1 | Draft 2 | Typographical error in Solution Requirements ("the all") | Michael Mirmak | 2
8 | Draft 3 | Draft 23 | Add support option for components/designators that are not associated with IBIS files | Walter Katz
9 | Draft 3 | Draft 23 | Cross-check of EMD specification vs. example converted from JEDEC BRD file | Walter Katz
10 | Draft 3 | Draft 23 | Add Part Number field to designator list | Walter Katz |  | Now part of EMD Parts
11 | Draft 3 | Draft 7 (with revisions) | Add [EMD Parts] keyword definition text | Walter Katz
12 | Draft 3 | Draft 3 (as [Voltage List]) | Add [Rail Voltages] keyword definition text | Walter Katz
13 | (confirm draft #) | Draft 23 | Add new usage rules for Pin_Rail in Table 41 (e.g., *.y additional representation under Pin_Rail) | Bob Ross |  | Page 27
14 | (???) | Draft 8 | Add "typ", "min", "max" corner definitions for [Voltage List] keyword | Bob Ross
15 |  | Draft 24 | Verify first occurrence of "CAD" plus definition in IBIS | Michael Mirmak | 12 EMD Introduction; CAD does not appear in IBIS
16 |  | Draft 24 | Verify usages of "Interconnect Model" vs. "Electrical Model" | Michael Mirmak | Interconnect Model - 3; Electrical Model - 7 (4 of them refer to ISS or Touchstone)
17 |  | Draft 23 | Scrub use of phrase "tells the parser" - is this IBISCHK or EDA parser? What is being "told"? | Michael Mirmak |  | Noted in Known Issues List for IBIS
18 | (confirm draft #) | Draft 23 | What happens when a part in the part map is not associated with an IBIS file or EMD file? | Walter Katz |  | P. 11
19 |  | Draft 23_MM | Ensure only [EMD Parts] or [EMD Part Map] (not both) is used | Michael Mirmak | [EMD Part Map] not used
20 | (confirm draft #) | Draft 23 | Revise section on connection rules for EMD Group, EMD Set, and EMD Model | Bob Ross |  | Section 13.6
21 | Draft 8 | BIRD202.2 Draft 6 | Review [Voltage List] definition relative to rest of document | Randy Wolff
22 | Draft 9 | BIRD202.2 Draft 7 | Resolve matching between [Voltage Range] and [Voltage List] | Randy Wolff
23 |  | Draft 29 | Search for use of "pin name" and "pin_name" to clarify potential confusion vs. "signal name" | Walter Katz
24 |  | Draft 29 | Is there a definition of Designator Pin? | Michael Mirmak | (from draft 17) | No; see comments in Draft 24
25 |  | Draft 29 | Clarify use of "associated" throughout documentand define "connected" early in the document vs. shorting (all contexts; examine Terminal section specifically) | Walter Katz | (from draft 21)
26 | Draft 23 | Draft 23 | i.a.iv in 13.6 supports cascaded Model blocks? E.g. three duplicated pin names at one interface | Bob Ross | (from draft 17)
27 |  |  | Check all cross-references to "Section" numbers | Michael Mirmak
28 |  | Draft 29 | Check for ".emd file" vs. "EMD file" in context | Michael Mirmak
29 |  | Draft 29 | Update keyword hierarchy (before final editorial pass) | Bob Ross
30 |  |  | Final editorial pass (e.g., capitalization of "pin" and "pins") | Michael Mirmak