## Sheet1
# | Draft Implemented | Draft Verified | Task | Subtask | Original Document | 180727 Draft Page | 180816 Draft Page (All Markup) | 180820 Draft Page (All Markup) | 180824 Draft Page (All Markup) | 180829 Draft Page (All Markup) | 180905 Draft Page (All Markup) | 181019 Draft Page (All Markup)
Fold in Known Issues for Ver6_1
1 | (implies change to global numbering of sections AND revision of "GENERAL RESERVED PARAMETERS" section) | 181030 | 1 | Muranyi | page 202 | 214
2 | 180727 | 180727 | 2 | Clark | page 56 | 65
3 | 180816 | 180816 | 3 | Muranyi | page 193 | 210 | 210
4 | 180816 | 180816 | 4 | Mirmak | page 28,65[, 257] |  | 41, 78, 291
5 | 180817 | 180817 | 5 | Biernacki | page 235,236 |  | (255; see also #21 below)
6 | 180816 | 180817 | 6 | Clark | page 232,234,235,237 |  | 251, 253, 254, 256
7 | 180816 | 180817 | 7 | Clark | page 242 |  | 261
8 | 180727 | 180817 | 8 | Ross | page 4 |  | 7
9 | (requires changes to node, terminal, etc. language) | 180824 | 9 | Ross | page 72 |  | 85
10 | 180816 | 180820 | 10 | Mirmak | page 41 |  | 54
11 | 180816 | 180820 | 11 | Mirmak | page 180 |  | 197
12 | 180816 | 180820 | 12 | Clark | page 78 |  | 91
13 | 180816 | 180820 | 13 | Biernacki | leading caps after formulas |  | 198,235,236,240,243,244,245,289,292
14 | 180816 | 180820 | 14 | Clark | page 226 |  | 244,245
15 | 180816 | 180820 | 15 | Muranyi | page 245 |  | 264
16 | 180816 | 180822 | 16 | LaBonte | page 172,193 |  | 189, 210
17 | 180816 | 180820 | 17 | Muranyi | page 126 |  | 131
18 | 180816 | 180820 | 18 | Muranyi | page 142 (should be 143 in PDF) |  | 158
19 | 180816 | 180820 | 19 | Muranyi | page 104 |  | 117
20 | 180816 | 180822 | 20 | Mirmak | page 172,193 |  | 189
21 | withdrawn |  | 21 | Ross | page 235,236 |  | 255
22 | 180816 | 180822 | 22 | Muranyi | page 110,123 |  | 123, 138
23 | 180816 | 180822 | 23 | Ross | page 193 |  | 210
Fold in BIRDs (try from back to front to preserve earlier page number references such as working on the IBIS-AMI changes first and then the earlier sections.
24 | 180816 | 180829 | 1 | BIRD147.6 Back-channel Support |  |  | 187-188, 266-274
25 | 180816 | 180829 | 2 | BIRD158.7 AMI Touchstone (R) Analog Buffer Models (Superseded by BIRD194 below) |  |  | 275-279
26 | 180816 | 180829 | 3 | BIRD165.1 Parameter Passing Improvements for [External Circuit] Package Models with [Circuit Call] |  |  | 144 |  |  | 107,144,145,150
27 | 180816 | 180905 | 4 | BIRD179 New IBIS-AMI Reserved Parameter Special_Param_Names |  |  | 225-227 |  |  |  | 226-228
28 | 180816 | 180905 | 5 | BIRD180 Require Unique Pin_Names in [Pin] |  |  | 26 |  |  |  | 26
29 | 180816 | 180905 | 6 | BIRD182 POWER and GND [Pin] signal_name as [Pin Mapping] bus_label |  |  | 34-35 |  |  |  | 34-35
30 | 180816 | 180905 | 7 | BIRD183 [Model Data] Matrix Subparameter Terminology Correction |  |  | 20,21,162 |  |  |  | 20,21,163
31 | 180816 | 180905 | 8 | BIRD184.2 Model_name and Signal_name Restriction for POWER and GND Pins |  |  | 26 |  |  |  | 26
32 | 180816 | 180905 | 9 | BIRD185.2 Section 3 Reserved Word Guideline Update |  |  | 13-14 |  |  |  | 13
33 | 180816 | 180926 | 10 | BIRD186.4 File Naming Rules |  |  | 15, 23, 106, 113-114, 133-136, 139-142
34 | 180816 | 180928 | 11 | BIRD187.3 Format and Usage Out Clarifications |  |  | 213-214, 218
35 | 180816 | 180928 | 12 | BIRD188.1 Expanded Rx_Noise Support for AMI |  |  | 246-249
36 | 180816 | 181003 | 13 | BIRD189.7 Interconnect Modeling Using IBIS-ISS and Touchstone |  |  | 25, 28-34, 37-38, 154, 294-327
37 | 180816 | 181005 | 14 | BIRD191.2 Clarifying Locations for Si_Location and Timing_Location |  |  | 25
38 | 180816 | 181005 | 15 | BIRD192.1 Clarification of List Default Rules |  |  | 213
39 | 180816 | 180829 | 16 | BIRD193 Figure 29 Corrections |  |  | 145-149 |  |  | 144-150, 159
40 | 180816 | 180829 | 17 | BIRD194 Revised AMI Ts4file Analog Buffer Models |  |  | 275-279
Fold in Known Issues for BIRDs in Ver7.0_wip
41 | 180727 | 1801009 | 1 | Wolff (BIRD189.6) | page 28 | 305
42 | 180820 | 181016 | 2 | Biernacki (global) | connection to "Touchstone files", need proposed wording |  |  | 28, 301, 306
43 | 180820 | 1801009 | 3 | Butterfield (BIRD189.7) | page 41 |  |  | 318
44 | 180820 | 1801009 | 4 | Ross (BIRD189.7) | page 24 |  |  | 301
45 | 180820 | 1801009 | 5 | Ross (BIRD189.7) | page 26, need to review format column |  |  | 303
46 | 180820 | 1801009 | 6 | Ross (BIRD194) | page 6 |  |  | 279
47 |  |  | 7 | Treatment of plurals and possessives for keywords, AMI parameters, and reserved words - e.g., [Algorithmic Model]'s, [Algorithmic Model]s | Moved to finalization
48 |  |  | 8 | Capitalization of unique concepts to be universal? E.g., Reserved Parameters vs. reserved parameters | Moved to finalization
49 | 180824 | 180824 | 9 | TS4file vs. "Tstonefile" (Model_Specific) throughout document, including examples and text |  |  |  |  | 127, 141, 150, 198
50 | 181009 | 181009 | 10 | "Pin terminal" language appears at least four times | (search for phrase)
51 | 181010 | 181010 | 11 | Clarify "These keywords also support using each rail terminal individually " pg. 35
52 | 181010 | 181010 | 12 | The phrase "a single terminal that connects terminals that connects rails" needs clarification | (search for phrase)
53 | 181010 | 181010 | 13 | Is empty stem permitted (e.g., .ami) as a file name? | (global) Section 3.2 item 3 prohibits this
54 |  | 181016 | 14 | Check for consistent Converter Parameters syntax rules where phrase "a stem and an ending period" is used. This implements BIRD 196.1. | (search for phrase)
55 | 180829 | 180829 | 15 | Check for use of "xxx" extension language (use of quotes around three-character string)
56 |  | 181016 | 16 | Check for text explanation of "relative path" with example in core .ibs (as opposed to .ami or .ebd)
57 | 180928 | 181023 | 17 | Resolve redundant text in "10.6.1 RECEIVER RECOVERED CLOCK RESERVED PARAMETERS"
58 | 180928 | 181026 | 18 | Should AMI parameter summary tables be their own subsections? | Yes; reflected in 181024
59 | 181019 | 181026 | 19 | Correct "Rx_Receiver_Sensivity" (spelling) | [7 empty] | 250
60 | 181019 | 181026 | 20 | Add "API" definition on first use | [7 empty] | 192
61 | 181107 | 181109 | 21 | Re-examine NA vs. None for Rx_Clock_PDF Default | Expanded to all Default and Required column entries
62 | 181031 | 181107 | 22 | Revise Section 1.0 to streamline description of updates. | (offline)
63 | 181107 | 181107 |  | Resolve whether [Comment Char] is permitted to appear BEFORE [IBIS Ver] in .ibs., .ebd, .pkg, .ims files
Create two new sections or chapters for BCI and Interconnect Models
64 | 180727 | 181017 | 1 | BCI section |  | 266ff
65 | 180727 | 181017 | 2 | Interconnect section |  | 294ff
General Finalization
66 | 181026 | 181109 | 1 | Update the AMI section tables with all new IBIS-AMI parameters
67 | 181026 | 181109 | 2 | Update Section 10.8 with the new AMI parameters | Now Section 10.12 | [6 empty] | 274ff
68 | 181026 |  | 3 | Update Table and Figure Caption numbers/references as needed due to new information | Tables are done; Figures need checking
69 | 181109 |  | 4 | Update Section 3.1 Tree by deleting some subparameters per BIRD183 | Some updates in 180727; Bob Ross provided updated table Nov. 9 | 20, 21
70 | 180727 | 181109 | 5 | Add to Section 2.0 – the new BIRDs for V7.0 and number of BIRDs |  | 11, 12
71 |  |  | 6 | Update Versions 6.1 -> 7.0, Full dates first, then years only 2015 -> 2018 and Copyright years, all embedded throughout the document. | Should be very final step, for dates/years
72 |  |  | 7 | Issue new correction BIRD(s), if needed, identified as a result of the editorial pass and include them | Should be the next-to-last step, at Open Forum review
73 | 181107 | 181109 | 8 | Update capitalization/bold of sections, headings, and cross-references to sections | Partially done in 181019
74 | 181030 |  | 9 | Update Table of Contents (paying attention to capitalization and indentation) | Fix Heading 2 to remove indent globally
75 | 181109 |  | 10 | Ensure references to Section 3.2, item 3 of "Syntax Rules" refers to file names; ensure Section 3, "General Syntax Rules and Guidelines" refers to more general rules.
76 | 181019 |  | 11 | "Chapter" is now "Section", globally
77 | 181107 | 181107 | 12 | Placement of [End] in Section 4 with renamed section title? Or at end of another section?
78 | 181107 | 181107 | 13 | Expand [IBIS Ver] text to mention other supported file types.
79 |  |  | 14 | Check table widths for margin encroachment and left alignment
80 | 181026 |  | 15 | Renumber tables after Table 36 (consider auto-numbering)
81 |  |  | 16 | Treatment of plurals and possessives for keywords, AMI parameters, and reserved words - e.g., [Algorithmic Model]'s, [Algorithmic Model]s | (global)
82 |  |  | 17 | Capitalization of unique concepts to be universal? E.g., Reserved Parameters vs. reserved parameters | (global)
83 |  |  | 18 | Check vertical spacing througout document (after each paragraph) | (global)
| 181107 |  | 19 | Add BIRD196 to the BIRD list | Section 2.0