## Sheet1
Task | Draft Implemented | Draft Verified | Subtask | Owner | Pages from Original Document
1 |  |  | Clarify use of "connected" throughout document (e.g., use of signal_names, distinction vs. "shorted") | Bob Ross
2 |  |  | Adding structural diagrams of an EMD (three), featuring extended net examples (text on page 7) | Randy Wolff
3 |  |  | EMD Model and Supply Pin Connections - replace "Pins may be terminals…" with new section from owner | Bob Ross | 26
4 |  |  | List of key terms and definitions | Michael Mirmak
5 |  |  | Check of syntax of examples throughout the document | (all)
6 |  |  | Reorder rules in [EMD Group] (e.g., I/O pin_name rules) to appear after the definitions of terms used | Bob Ross | 14, 15
7 | Draft 1 | Draft 2 | Typographical error in Solution Requirements ("the all") | Michael Mirmak | 2
8 | Draft 3 |  | Add support option for components/designators that are not associated with IBIS files | Walter Katz
9 | Draft 3 |  | Cross-check of EMD specification vs. example converted from JEDEC BRD file | Walter Katz
10 | Draft 3 |  | Add Part Number field to designator list | Walter Katz
11 | Draft 3 | Draft 7 (with revisions) | Add [EMD Parts] keyword definition text | Walter Katz
12 | Draft 3 | Draft 3 (as [Voltage List]) | Add [Rail Voltages] keyword definition text | Walter Katz
13 |  |  | Add new usage rules for Pin_Rail in Table 41 (e.g., *.y additional representation under Pin_Rail) | Bob Ross
14 | (???) | Draft 8 | Add "typ", "min", "max" corner definitions for [Voltage List] keyword | Bob Ross
15 |  |  | Verify first occurrence of "CAD" plus definition in IBIS | Michael Mirmak
16 |  |  | Verify usages of "Interconnect Model" vs. "Electrical Model" | Michael Mirmak
17 |  |  | Scrub use of phrase "tells the parser" - is this IBISCHK or EDA parser? What is being "told"? | Michael Mirmak
18 |  |  | What happens when a part in the part map is not associated with an IBIS file or EMD file? | Walter Katz
19 |  |  | Ensure only [EMD Parts] or [EMD Part Map] (not both) is used | Michael Mirmak
20 |  |  | Revise section on connection rules for EMD Group, EMD Set, and EMD Model | Bob Ross
21 | Draft 8 |  | Review [Voltage List] definition relative to rest of document | Randy Wolff
22 | Draft 9 |  | Resolve matching between [Voltage Range] and [Voltage List] | Randy Wolff
|  |  | Search for use of "pin name" and "pin_name" to clarify potential confusion vs. "signal name" | Walter Katz
|  |  | Is there a definition of Designator Pin? | Michael Mirmak | (from draft 17)
|  |  | Clarify use of "associated" throughout document (distinction vs. "connected") | Walter Katz | (from draft 20)
|  |  | i.a.iv in 13.6 supports cascaded Model blocks? E.g. three duplicated pin names at one interface | Bob Ross | (from draft 17)
|  |  | Update keyword hierarchy (before final editorial pass) | Bob Ross
|  |  | Final editorial pass (e.g., capitalization of "pin" and "pins") | Michael Mirmak